## Slide 1: Selenium Automation
Web Portal

## Slide 2: What is Automation?
In software testing, test automation is the use of special software (separate from the software being tested) to control the execution of tests and the comparison of actual outcomes with predicted outcomes.
Test automation can automate some repetitive but necessary tasks in a formalized testing process already in place, or perform additional testing that would be difficult to do manually.
Test automation is critical for continuous delivery and continuous testing.

## Slide 3: Why Automation ?
Automation
Execution of repeated testcases
Enables parallel Execution
Saves Time and Money
Improves accuracy
Enables Scheduled Execution
Encourages Unattended Execution

## Slide 4: What is Selenium ?

## Slide 5: Why Selenium ?
Selenium
Open Source
Web-Based Automated Testing
Multiple Frameworks
Regular repository developments
Multiple Browsers
Multiple Programming Languages

## Slide 6: Framework Design
Controller
Drivers
Libraries
Scripts
TEST
DATA
Input
Output
AUT
OTP
RESULTS
Test Execution
Log Files
Screenshots
MYSQL
SELENIUM
CODE REPOSITORY
GITHUB
CIT- JENKINS
One at a time
Parallel
Scheduled

## Slide 7: Our Approach
The plan is to divide the overall automation of web portal through selenium in several phases. This agile approach will enable the best quality of automation scripts. The scripts can be run by end of each phase to test the covered functionalities. We shall divide the automation project in 7 phases as listed below –
Phase 1: Automation Framework Design
Phase 2: Develop scripts for most frequently used screens
Phase 3: Develop scripts for remaining screens of the portal
Phase 4: AMC
Phase 5: Develop Smoke Testing Suite
Phase 6: Automate PRO
Phase 7: Complete Integration and End to End Testing
Done few things remaining
In Progress
Not Started
Not Started
Not Started
Not Started
Done few things remaining

## Slide 8: Phase 1: Automation Framework Design
This will involve following activities-
Basic framework for designing the test script for member pages
Creating the controller
Creating the test data file
Creating the initializer
Creating logger to trace errors if any
Automated email notification
Test results/reports – Database + HTML Report
Scheduled Test Run
Parallel Execution
 Done
 Done
 Done
 Done
 Done
 Not Started
 In Progress
 Done
 Done

## Slide 9: Phase 2: Automate most frequently used screens
This will involve developing scripts for most frequently used screens along with thorough Unit Testing. Automation framework may get updated in this phase.
Staff
Patients
Record Activity
Schedules
Portal Users
Closed Activities
 Done
 Done
 Done few things remaining
 Done
 In Progress
 Done few things remaining

## Slide 10: Phase 3: Develop remaining scripts for OTP
This will involve developing scripts for remaining screens of the portal OTP. Some of them are listed below –
Admin – Member screens (Portal Users, External HCTP Users, POI)
Admin – Activity screens (Alerts, Care Manager Forms)
Admin – Reports (Time and Distance, Travel Source Comparison etc.)
Admin – User Roles, Address Book setup, Messaging etc.

## Slide 11: Phase 4: AMC
Analyze AMC screens
Create manual test cases
Automate manual test cases
Test and integrate

## Slide 12: Phase 5: Smoke Testing Suite
This will involve building Smoke Testing Suite that can be used for any site. There may be two Smoke Test Suite –
Quick Smoke Testing Suite: It will have some basic sanity checks to perform to validate any site.
Detail Smoke Testing Suite: It may cover the existing QA checklist meant for validating any new site creation.
  Feasibility analysis is required due to data dependency
  Analysis of different configurations

## Slide 13: Phase 6: Automate PRO
Analyze PRO screens
Create manual test cases
Automate manual test cases
Test and integrate

## Slide 14: Phase 7: Integration and End to End Testing
This would be the last phase of Automation but of course there will be always be some maintenance work going forward. In this phase we are targeting –
Complete Integration
End to End Testing

## Slide 15
Phase 2
Phase 4
Phase 3
CellTrak Automation Plan and Progress |  |  |  |  |  |  |  |  | 
Module | Manual |  |  |  |  | Automation |  |  | 
 | Estimated manual testcases for Selenium (Based on existing Regression testcases) | Final (Actual) manual testcases for Selenium |  | Status of manual testcases creation for Selenium | Expected Date to complete manual testcases for Selenium | Testcases automated as of Sep 15, 2017 | % Automation Out of available testcases | Expected date to complete testcase automation | 
Staff | 50 | 71 |  | Complete | 5-Jul-17 | 71 | 100% | 28-Jul-17 | 
Patients | 50 | 59 |  | Complete | 7-Jul-17 | 59 | 100% | 28-Jul-17 | 
Record Activity | 41 | 41 |  | Complete | 26-Jul-17 | 41 | 100% | 15-Aug-17 | 
Schedules | 50 | 54 |  | Complete | 14-Jul-17 | 54 | 100% | 2-Aug-17 | 
Portal Users | 50 | 51 |  | Complete | 3-Aug-17 | 51 | 100% | 8-Sep-17 | 
Closed Activities | 50 | 50 |  | In Review | 11-Aug-17 | 24 | 48% | 20-Nov-17 | 
AMC | 160 | 160 |  | In Progress | 6-Oct-17 |  |  |  | 
Alerts | 110 | 0 |  | Not Started | 18-Aug-17 | 0 | 0% | 31-Dec-17 | 
User Roles | 90 | 0 |  | In Progress | 28-Aug-17 | 0 | 0% | 31-Jan-18 | 
Messaging | 50 | 0 |  | Not Started | 8-Sep-17 | 0 | 0% | 31-Jan-18 | 
PRO | 180 | 0 |  | Not Started |  | 0 | 0% |  | 
Maps | 40 | 0 |  | Not Started | 15-Sep-17 | 0 | 0% | 5-Mar-18 | 
Total | 881 | 486 |  |  |  | 300 |  |  | 
Note: Final Testcases are based on 5.7.IVR Release. |  |  |  |  |  |  |  |  | 
Legend for "Status of Manual Test Case Creation" |  |  |  |  |  |  |  |  | 
Complete |  |  | All test cases created, and available for automation coding. |  |  |  |  |  | 
In progress |  |  | Test case creation in progress. |  |  |  |  |  | 
In Review |  |  | Test case creation completed by non-QA resource (intern); being reviewed for correctness by QA team. |  |  |  |  |  | 
Not Started |  |  | Test case creation has not started. |  |  |  |  |  | 

## Slide 16: Thank You
QA Team